## Sheet1
sl no | Tasks - cloud | owner | Status | Comment
1 | App repo | Mahendra | Done
3 | s3 | Mahendra | Done
4 | lb+ec2 - size - enginFrame | Mahendra | Done
5 | my sql rds | Mahendra | Done
6 | netgroup | Mahensh Deshmukh | Done
7 | domain registration | Mahendra S | Pending | DNS Maping
8 | certificates | Mahendra S | Done | Import is pending - raised a PR
9 | oidc | Mahesh Deshmukh | Pending
10 | Firewall - license servers outbound | Mahendra | Done for us-east-1 | Need to raise for Ohio
11 | Submit NTI for SNOWBALL | Venu T
12 | subnet creation using account repo | Yasen
13 | NatGW | Yasen
14 | FSX - and creating volumes | Yasen
15 | App team fed role | Yasen
17 | ticket with CoreTech to seek CIDR range for GreeView | Yasen
18 | Firewall - SMB, DCV - Inbound | Mahendra | Pending
19 | setup/creation for HeadNode, data mover, login nodes, ssh (Bastion - server) | Yasen |  | Pending on new subnet - task 12
20 | ASG with DCV Gateways
21 | HPC oneClick setup - adopting AWS CFT to Landing Zone | Yasen